## Sheet1
	General Activities	Specific Activities	Finished?
July
3rd Week	Team Registration and Managerial Stage
4th Week	General Mechanics and World Design Stage
August
1st Week
2nd Week
3rd Week	Specific Mechanics and Level Design Stage
4th Week
September
1st Week
2nd Week
3rd Week	Class Structures and Heirarchies Design Stage
4th Week
October
1st Week
2nd Week
3rd Week
4th Week
November	Art, Music, and Code Development Stage
1st Week
2nd Week
3rd Week
4th Week
December
1st Week
2nd Week
3rd Week
4th Week
January
1st Week
2nd Week
3rd Week	Testing, Debugging, and Fine Tuning Stage
4th Week
February
1st Week
2nd Week
3rd Week
4th Week
March
1st Week	Early Documentation Stage
2nd Week	March 7 - 1st Round Deadline
3rd Week	Source Clean-up Stage
4th Week	March 28 - 2nd Round Begins
April	Improvements Based on Feedback Stage
1st Week
2nd Week
3rd Week
4th Week	April 25 - 2nd Round Ends
May	Final Changes and Late Documentation Stage
1st Week
2nd Week
3rd Week
4th Week
June
1st Week
2nd Week
3rd Week
4th Week
July
1st Week	3rd Round Begins
2nd Week