## Sheet1
	General Activities	Specific Activities	Finished?
July
3rd Week	Team Registration and Managerial Stage	clear team roles, install git, join github, join IC	yes
4th Week	General Mechanics and World Design Stage	basic premise	yes
August		basic storyline	yes
1st Week		basic world design	yes
2nd Week
3rd Week	Specific Mechanics and Level Design Stage	mechanics	yes
4th Week
September		Initial Design	somewhat
1st Week		terminology	yes
2nd Week		complete story
3rd Week	Class Structures and Heirarchies Design Stage	Expanded Design
4th Week		UML diagrams
October		state diagrams
1st Week
2nd Week		team logo and game logo
3rd Week
4th Week		early prototype
November	Art, Music, and Code Development Stage
1st Week		learning phase
2nd Week
3rd Week		develop DLLs
4th Week
December		develop basic skeleton
1st Week
2nd Week		develop complex algorithms required
3rd Week
4th Week		develop GUI
January
1st Week		code cleanup and efficiency tuning
2nd Week		complete early graphics and sounds
3rd Week	Testing, Debugging, and Fine Tuning Stage
4th Week
February
1st Week
2nd Week
3rd Week
4th Week
March
1st Week	Early Documentation Stage
2nd Week	March 7 - 1st Round Deadline
3rd Week	Source Clean-up Stage
4th Week	March 28 - 2nd Round Begins
April	Improvements Based on Feedback Stage
1st Week
2nd Week
3rd Week
4th Week	April 25 - 2nd Round Ends
May	Final Changes and Late Documentation Stage
1st Week
2nd Week
3rd Week
4th Week
June
1st Week
2nd Week
3rd Week
4th Week
July
1st Week	3rd Round Begins
2nd Week